## APPM-Assessment
Agile Product & Project Management Assessment
Category | No. | Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Score | Avg.
Iteration and Adaptation | 1 | Does your program deliver useful content for business review every 2 weeks? | x | [6 empty] | 1 | 3
| 2 | Does your program's change management process encourage worthwhile change submissions? |  | x | [5 empty] | 2
| 3 | Is your program's (feature) backlog reprioritized after every program increment or release? |  |  | x |  |  |  |  | 3
| 4 | Are retrospectives held at the end of each iteration, program increment, or release? |  |  |  | x |  |  |  | 4
| 5 | Does your program continuously improve program processes to minimize waste and inefficiency? |  |  |  |  | x |  |  | 5
Planning and Collaboration | 6 | Is your program's work planned and prioritized based upon the business value of features? | [5 empty] | x |  | 6 | 5.6
| 7 | Does your program define near-term features with greater detail than long-term features? | [6 empty] | x | 7
| 8 | Is your program willing to tradeoff planned features for new change requests and rework? | [5 empty] | x |  | 6
| 9 | Are business owners and customers involved in estimating the program's feature backlog? |  |  |  |  | x |  |  | 5
| 10 | Does your program backlog contain features or stories for iterative refactoring or rework? |  |  |  | x |  |  |  | 4
Empowerment and Rewards | 11 | Do program teams self-select their own features and user stories most of the time? |  |  | x |  |  |  |  | 3 | 2.2
| 12 | Do program teams determine how to best organize and execute their own work? |  | x | [5 empty] | 2
| 13 | Do program teams have a clear voice in making program level decisions and tradeoffs? | x | [6 empty] | 1
| 14 | Do program teams get recognized for effort, accomplishments, and innovations at team-level? |  | x | [5 empty] | 2
| 15 | Do program teams recieve and evenly distribute any recognitions, rewards, or remunerations? |  |  | x |  |  |  |  | 3
Controls and Practices | 16 | Are automated integration, testing, deployment, and remediation encouraged, rewarded, and in place? |  |  |  | x |  |  |  | 4 | 5.6
| 17 | Are program teams encouraged to keep processes and documentation to a "value-adding sufficient"? |  |  |  |  | x |  |  | 5
| 18 | Does your program use metrics such as feature progress, release burndown, business value, etc.? | [5 empty] | x |  | 6
| 19 | Does your program teams have an open work environment that supports collaboration and conversation? | [6 empty] | x | 7
| 20 | Does your program use visible information radiators to display planning, tracking, and status information? | [5 empty] | x |  | 6
Context and Uncertainty | 21 | Does your program tailor its program increment, release, and iteration length (as needed)? |  |  |  |  | x |  |  | 5 | 3
| 22 | Does your program select lean and agile ceremonies, practices, tools, and metrics (as needed)? |  |  |  | x |  |  |  | 4
| 23 | Does your program select, tailor, and refine its team size and composition (as needed)? |  |  | x |  |  |  |  | 3
| 24 | Does your program select, tailor, and refine its automated technical tools (as needed)? |  | x | [5 empty] | 2
| 25 | Does your program select, tailor, and refine its processes based on mission criticality? | x | [6 empty] | 1