## Agile Readiness
Agile Product & Project Readiness Assessment
Category | No. | Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Score | Avg.
Agile Management Office | 1 | The agile team of teams has a leader (Program Manager, Project Manager, Agile Management Office Leader, etc.) | [7 empty] | 1 | 4.1429 | bar: 1
| 2 | The agile management office leader is trained and certified | [7 empty] | 2 | bar: 2
| 3 | The agile management office leader has agile management office experience | [7 empty] | 3 | bar: 3
| 4 | The agile management office leader forms an agile governance or operating team | [7 empty] | 4 | bar: 4
| 5 | The agile management office leader ensures the agile governance or operating team is trained and certified | [7 empty] | 5 | bar: 5
| 6 | The agile management office leader ensures the agile governance or operating team is experienced | [7 empty] | 6 | bar: 6
| 7 | The agile management office leader ensures there is a clear vision, goals, canvas, roadmap, etc. | [7 empty] | 7 | bar: 7
| 8 | The agile management office leader ensures there is a team of teams leader | [7 empty] | 6 | bar: 6
| 9 | The agile management office leader ensures a team of teams is formed with agile teams no more than 10 people | [7 empty] | 5 | bar: 5
| 10 | The agile management office leader ensures there is a product management team | [7 empty] | 4 | bar: 4
| 11 | The agile management office leader ensures there is a product management backlog with features | [7 empty] | 3 | bar: 3
| 12 | The agile management office leader ensures an agile framework is selected (SAFe, Spotify, LeSS, SoS, etc.) | [7 empty] | 2 | bar: 2
| 13 | The agile management office leader ensures team of team members are trained and certified in the agile framework | [7 empty] | 1 | bar: 1
| 14 | The agile management office leader ensures team of team members are experienced in the agile framework | [7 empty] | 2 | bar: 2
| 15 | The agile management office leader ensures team of team members apply the agile framework events | [7 empty] | 3 | bar: 3
| 16 | The agile management office leader ensures agile framework performance is measured and improving | [7 empty] | 4 | bar: 4
| 17 | The agile management office leader ensures subcontracts are in place to support agile framework delivery | [7 empty] | 5 | bar: 5
| 18 | The agile management office leader ensures subcontractors are assigned to the agile team of teams | [7 empty] | 6 | bar: 6
| 19 | The agile management office leader ensures the team of teams apply agile lifecycle management tools | [7 empty] | 7 | bar: 7
| 20 | The agile management office leader ensures the team of teams applies agile performance measures | [7 empty] | 6 | bar: 6
| 21 | The agile management office leader ensures the team of teams is continuously improving and adding value | [7 empty] | 5 | bar: 5
Agile Team of Teams Leader | 22 | The agile team of teams has a leader (Chief Scrum Master, Release Train Engineer, Tribe Leader, etc.) | [7 empty] | 4 | 3.5263 | bar: 4
| 23 | The agile team of teams leader is trained and certified | [7 empty] | 3 | bar: 3
| 24 | The agile team of teams leader has agile team of teams experience | [7 empty] | 2 | bar: 2
| 25 | The agile team of teams leader ensures there is a product management team | [7 empty] | 1 | bar: 1
| 26 | The agile team of teams leader ensures there is a team of teams backlog with features | [7 empty] | 2 | bar: 2
| 27 | The agile team of teams leader facilitates product management | [7 empty] | 3 | bar: 3
| 28 | The agile team of teams leader is an integral part of an agile management office | [7 empty] | 4 | bar: 4
| 29 | The agile team of teams leader ensures agile teams are trained and certified | [7 empty] | 5 | bar: 5
| 30 | The agile team of teams leader ensures all agile teams are on the same cadence | [7 empty] | 6 | bar: 6
| 31 | The agile team of teams leader ensures team of team events occur (quarterly planning, system demos, inspect & adapt, etc.) | [7 empty] | 7 | bar: 7
| 32 | The agile team of teams leader organizes into agile teams of no more than 10 people | [7 empty] | 6 | bar: 6
| 33 | The agile team of teams leader ensures each agile team has a designated product owner and Scrum master | [7 empty] | 5 | bar: 5
| 34 | The agile team of teams leader ensures agile teams are trained and certified | [7 empty] | 4 | bar: 4
| 35 | The agile team of teams leader ensures agile teams are experienced | [7 empty] | 3 | bar: 3
| 36 | The agile team of teams leader ensures agile teams have product backlogs | [7 empty] | 2 | bar: 2
| 37 | The agile team of teams leader ensures agile teams apply agile events | [7 empty] | 1 | bar: 1
| 38 | The agile team of teams leader ensures agile teams apply agile lifecycle management tools | [7 empty] | 2 | bar: 2
| 39 | The agile team of teams leader ensures the team of teams applies agile performance measures | [7 empty] | 3 | bar: 3
| 40 | The agile team of teams leader ensures team of teams are continuously improving and adding value | [7 empty] | 4 | bar: 4
Agile Product Management | 41 | The agile team of teams has a designated agile product manager | [7 empty] | 5 | 4.3 | bar: 5
| 42 | The agile product manager is trained and certified | [7 empty] | 6 | bar: 6
| 43 | The agile product manager has agile team of teams experience | [7 empty] | 7 | bar: 7
| 44 | The agile product manager forms a vision, goals, canvas, and roadmap | [7 empty] | 6 | bar: 6
| 45 | The agile product manager forms a team of teams backlog with features and acceptance criteria | [7 empty] | 5 | bar: 5
| 46 | The agile product manager prioritizes the team of teams backlog (features) | [7 empty] | 4 | bar: 4
| 47 | The agile product manager refines the team of teams backlog | [7 empty] | 3 | bar: 3
| 48 | The agile product manager participates in agile team of team events | [7 empty] | 2 | bar: 2
| 49 | The agile product manager empowers the agile team of teams | [7 empty] | 1 | bar: 1
| 50 | The agile product manager shares risks and responsibility for success | [7 empty] | 2 | bar: 2
| 51 | The agile product manager is trained to use an agile lifecycle management tool (JIRA, Align, etc.) | [7 empty] | 3 | bar: 3
| 52 | The agile product manager applies an agile lifecycle management tool to manage team of teams backlogs | [7 empty] | 4 | bar: 4
| 53 | The agile product manager ensures each agile team has a designated product owner | [7 empty] | 5 | bar: 5
| 54 | The agile product manager ensures product owners are trained and certified | [7 empty] | 6 | bar: 6
| 55 | The agile product manager ensures product owners are experienced | [7 empty] | 7 | bar: 7
| 56 | The agile product manager ensures product owners form product backlogs | [7 empty] | 6 | bar: 6
| 57 | The agile product manager ensures product owners refine product backlogs | [7 empty] | 5 | bar: 5
| 58 | The agile product manager ensures product owners apply agile lifecycle management tools | [7 empty] | 4 | bar: 4
| 59 | The agile product manager ensures the team of teams applies agile product management performance measures | [7 empty] | 3 | bar: 3
| 60 | The agile product manager ensures product management is continuously improving and adding value | [7 empty] | 2 | bar: 2
Product Owners | 61 | The agile teams have a designated product owner | [7 empty] | 1 | 3.7692 | bar: 1
| 62 | The product owners are trained and certified | [7 empty] | 2 | bar: 2
| 63 | The product owners have agile experience | [7 empty] | 3 | bar: 3
| 64 | The product owners identify a product goal | [7 empty] | 4 | bar: 4
| 65 | The product owners create a product backlog | [7 empty] | 5 | bar: 5
| 66 | The product owners refine the product backlog | [7 empty] | 6 | bar: 6
| 67 | The product owners participate in agile events | [7 empty] | 7 | bar: 7
| 68 | The product owners empower the agile teams | [7 empty] | 6 | bar: 6
| 69 | The product owners share risks and responsibility for success | [7 empty] | 5 | bar: 5
| 70 | The product owners are trained to use an agile lifecycle management tool (JIRA, Align, etc.) | [7 empty] | 4 | bar: 4
| 71 | The product owners apply an agile lifecycle management tool to manage backlogs | [7 empty] | 3 | bar: 3
| 72 | The product owners apply product backlog performance measures | [7 empty] | 2 | bar: 2
| 73 | The product owners ensure the product backlog is continuously improving and adding value | [7 empty] | 1 | bar: 1
Scrum Masters | 74 | The agile teams have a designated Scrum master | [7 empty] | 2 | 3.8462 | bar: 2
| 75 | The Scrum masters are trained and certified | [7 empty] | 3 | bar: 3
| 76 | The Scrum masters have agile experience | [7 empty] | 4 | bar: 4
| 77 | The Scrum masters ensure backlog refinement occurs | [7 empty] | 5 | bar: 5
| 78 | The Scrum masters ensure sprint planning occurs | [7 empty] | 6 | bar: 6
| 79 | The Scrum masters ensure daily standups occur | [7 empty] | 7 | bar: 7
| 80 | The Scrum masters ensure sprint reviews occur | [7 empty] | 6 | bar: 6
| 81 | The Scrum masters ensure retrospectives occur | [7 empty] | 5 | bar: 5
| 82 | The Scrum masters coache the agile teams | [7 empty] | 4 | bar: 4
| 83 | The Scrum masters are trained to use an agile lifecycle management tool (JIRA, Align, etc.) | [7 empty] | 3 | bar: 3
| 84 | The Scrum masters apply an agile lifecycle management tool to manage backlogs | [7 empty] | 2 | bar: 2
| 85 | The Scrum masters ensure the agile team is applying agile performance measures | [7 empty] | 1 | bar: 1
| 86 | The Scrum masters ensure the agile team is continuously improving and adding value | [7 empty] | 2 | bar: 2
Agile Teams | 87 | There are agile teams of no more than 10 people | [7 empty] | 3 | 4 | bar: 3
| 88 | The agile teams are trained and certified | [7 empty] | 4 | bar: 4
| 89 | The agile teams have agile experience | [7 empty] | 5 | bar: 5
| 90 | The agile teams have a designated product owner | [7 empty] | 6 | bar: 6
| 91 | The agile teams have a designated Scrum master | [7 empty] | 7 | bar: 7
| 92 | The agile teams have a product backlog and goal | [7 empty] | 6 | bar: 6
| 93 | The agile teams form sprint backlogs with a goal | [7 empty] | 5 | bar: 5
| 94 | The agile teams perform agile events (planning, standups, reviews, retros, etc.) | [7 empty] | 4 | bar: 4
| 95 | The agile teams are trained to use an agile lifecycle management tool (JIRA, Align, etc.) | [7 empty] | 3 | bar: 3
| 96 | The agile teams apply an agile lifecycle management tool to manage backlogs | [7 empty] | 2 | bar: 2
| 97 | The agile teams apply agile performance measures | [7 empty] | 1 | bar: 1
| 98 | The agile teams are continuously improving and adding value | [7 empty] | 2 | bar: 2