## CMMI
Capability Maturity Model Integration© for Development Version 1.2 (CMMI-DEV-V1.2©)
Level | Process Area | Specific Goal | Specific Practice | Subpractice | Work Products (detailed) | Work Products (high-level)
1 | 0 | 0 | 0 | 0 | 0 | 0
2 | 7 | 15 | 56 | 219 | 139 | 15
3 | 11 | 28 | 92 | 420 | 239 | 29
4 | 2 | 3 | 13 | 62 | 28 | 4
5 | 2 | 4 | 11 | 60 | 16 | 4
Total | 22 | 50 | 172 | 761 | 422 | 52
Initial
1 | 0 | 0 | 0 | 0 | 0 | 0
Managed | Requirements Management (REQM) | Manage Requirements | Obtain an Understanding of Requirements | Establish criteria for distinguishing appropriate requirements providers | Lists of criteria for distinguishing appropriate requirements providers | Requirements management system
|  |  |  | Establish objective criteria for the evaluation and acceptance of requirements | Criteria for evaluation and acceptance of requirements
|  |  |  | Analyze requirements to ensure that the established criteria are met | Results of analyses against criteria
|  |  |  | Reach an understanding of the requirements with the requirements provider so that the project participants can commit to them | An agreed-to set of requirements
|  |  | Obtain Commitment to Requirements | Assess the impact of requirements on existing commitments | Requirements impact assessments
|  |  |  | Negotiate and record commitments | Documented commitments to requirements and requirements changes
|  |  | Manage Requirements Changes | Document all requirements and requirements changes that are given to or generated by the project | Requirements status
|  |  |  | Maintain the requirements change history with the rationale for the changes | Requirements database
|  |  |  | Evaluate the impact of requirement changes from the standpoint of relevant stakeholders | Requirements decision database
Make the requirements and change data available to the project
|  |  | Maintain Bidirectional Traceability of Requirements | Maintain requirements traceability to ensure that the source of lower level (derived) requirements is documented | Requirements traceability matrix
|  |  |  | Maintain requirements traceability from a requirement to its derived requirements and allocation to functions, interfaces, objects, people, processes, and work products | Requirements tracking system
Generate the requirements traceability matrix
|  |  | Identify Inconsistencies Between Project Work and Requirements | Review the project’s plans, activities, and work products for consistency with the requirements and the changes made to them | Documentation of inconsistencies including sources, conditions, and rationale
|  |  |  | Identify the source of the inconsistency and the rationale | Corrective actions
Identify changes that need to be made to the plans and work products resulting from changes to the requirements baseline
Initiate corrective actions
| Project Planning (PP) | Establish Estimates | Estimate the Scope of the Project | Develop a WBS based on the product architecture | Task descriptions | Estimates
|  |  |  | Identify the work packages in sufficient detail to specify estimates of project tasks, responsibilities, and schedule | Work package descriptions
|  |  |  | Identify product or product components that will be externally acquired | WBS
Identify work products that will be reused
|  |  | Establish Estimates of Work Product and Task Attributes | Determine the technical approach for the project | Technical approach
|  |  |  | Use appropriate methods to determine the attributes of the work products and tasks that will be used to estimate the resource requirements | Size and complexity of tasks and work products
|  |  |  | Estimate the attributes of the work products and tasks | Estimating models
Attribute estimates
|  |  | Define Project Lifecycle |  | Project lifecycle phases
|  |  | Determine Estimates of Effort and Cost | Collect the models or historical data that will be used to transform the attributes of the work products and tasks into estimates of the labor hours and cost | Estimation rationale
|  |  |  | Include supporting infrastructure needs when estimating effort and cost | Project effort estimates
|  |  |  | Estimate effort and cost using models and/or historical data | Project cost estimates
|  | Develop a Project Plan | Establish the Budget and Schedule | Identify major milestones | Project schedules | Project plan
|  |  |  | Identify schedule assumptions | Schedule dependencies
|  |  |  | Identify constraints | Project budget
Identify task dependencies
Define the budget and schedule
Establish corrective action criteria
|  |  | Identify Project Risks | Identify risks | Identified risks
|  |  |  | Document the risks | Risk impacts and probability of occurrence
|  |  |  | Review and obtain agreement with relevant stakeholders on the completeness and correctness of the documented risks | Risk priorities
Revise the risks as appropriate
|  |  | Plan for Data Management | Establish requirements and procedures to ensure privacy and security of the data | Data management plan
|  |  |  | Establish a mechanism to archive data and to access archived data | Master list of managed data
|  |  |  | Determine the project data to be identified, collected, and distributed | Data content and format description
Data requirements lists for acquirers and for suppliers
Privacy requirements
Security requirements
Security procedures
Mechanism for data retrieval, reproduction, and distribution
Schedule for collection of project data
Listing of project data to be collected
|  |  | Plan for Project Resources | Determine process requirements | WBS work packages
|  |  |  | Determine staffing requirements | WBS task dictionary
|  |  |  | Determine facilities, equipment, and component requirements | Staffing requirements based on project size and scope
Critical facilities/equipment list
Process/workflow definitions and diagrams
Program administration requirements list
|  |  | Plan for Needed Knowledge and Skills | Identify the knowledge and skills needed to perform the project | Inventory of skill needs
|  |  |  | Assess the knowledge and skills available | Staffing and new hire plans
|  |  |  | Select mechanisms for providing needed knowledge and skills | Databases (e.g., skills and training)
Incorporate selected mechanisms into the project plan
|  |  | Plan Stakeholder Involvement |  | Stakeholder involvement plan
|  |  | Establish the Project Plan |  | Overall project plan
|  | Obtain Commitment to the Plan | Review Plans That Affect the Project |  | Record of the reviews of plans that affect the project | Project plan commitment
|  |  | Reconcile Work and Resource Levels |  | Revised methods and corresponding estimating parameters (e.g., better tools and use of off-the-shelf components)
Renegotiated budgets
Revised schedules
Revised requirements list
Renegotiated stakeholder agreements
|  |  | Obtain Plan Commitment | Identify needed support and negotiate commitments with relevant stakeholders | Documented requests for commitments
|  |  |  | Document all organizational commitments, both full and provisional, ensuring appropriate level of signatories | Documented commitments
Review internal commitments with senior management as appropriate
Review external commitments with senior management as appropriate
Identify commitments on interfaces between elements in the project, and with other projects and organizational units so that they can be monitored
| Project Monitoring and Control (PMC) | Monitor Project Against Plan | Monitor Project Planning Parameters | Monitor progress against the schedule | Records of project performance | Project monitoring results
|  |  |  | Monitor the project's cost and expended effort | Records of significant deviations
Monitor the attributes of the work products and tasks
Monitor resources provided and used
Monitor the knowledge and skills of project personnel
Document the significant deviations in the project planning parameters
|  |  | Monitor Commitments | Regularly review commitments (both external and internal) | Records of commitment reviews
Identify commitments that have not been satisfied or that are at significant risk of not being satisfied
Document the results of the commitment reviews
|  |  | Monitor Project Risks | Periodically review the documentation of the risks in the context of the project’s current status and circumstances | Records of project risk monitoring
Revise the documentation of the risks, as additional information becomes available, to incorporate changes
Communicate risk status to relevant stakeholders
|  |  | Monitor Data Management | Periodically review data management activities against their description in the project plan | Records of data management
Identify and document significant issues and their impacts
Document the results of data management activity reviews
|  |  | Monitor Stakeholder Involvement | Periodically review the status of stakeholder involvement | Records of stakeholder involvement
Identify and document significant issues and their impacts
Document the results of the stakeholder involvement status reviews
|  |  | Conduct Progress Reviews | Regularly communicate status on assigned activities and work products to relevant stakeholders | Documented project review results
Review the results of collecting and analyzing measures for controlling the project
Identify and document significant issues and deviations from the plan
Document change requests and problems identified in any of the work products and processes
Document the results of the reviews
Track change requests and problem reports to closure
|  |  | Conduct Milestone Reviews | Conduct reviews at meaningful points in the project’s schedule, such as the completion of selected stages, with relevant stakeholders | Documented milestone review results
Review the commitments, plan, status, and risks of the project
Identify and document significant issues and their impacts
Document the results of the review, action items, and decisions
Track action items to closure
|  | Manage Corrective Action to Closure | Analyze Issues | Gather issues for analysis | List of issues needing corrective actions | Project monitoring corrective actions
Analyze issues to determine need for corrective action
|  |  | Take Corrective Action | Determine and document the appropriate actions needed to address the identified issues | Corrective action plan
Review and get agreement with relevant stakeholders on the actions to be taken
Negotiate changes to internal and external commitments
|  |  | Manage Corrective Action | Monitor corrective actions for completion | Corrective action results
Analyze results of corrective actions to determine the effectiveness of the corrective actions
Determine and document appropriate actions to correct deviations from planned results for corrective actions
| Supplier Agreement Management (SAM) | Establish Supplier Agreements | Determine Acquisition Type |  | List of the acquisition types that will be used for all products and product components to be acquired | Supplier agreements
|  |  | Select Suppliers | Establish and document criteria for evaluating potential suppliers | Market studies
|  |  |  | Identify potential suppliers and distribute solicitation material and requirements to them | List of candidate suppliers
|  |  |  | Evaluate proposals according to evaluation criteria | Preferred supplier list
|  |  |  | Evaluate risks associated with each proposed supplier | Trade study or other record of evaluation criteria, advantages and disadvantages of candidate suppliers, and rationale for selection of suppliers
|  |  |  | Evaluate proposed suppliers' ability to perform the work | Solicitation materials and requirements
Select the supplier
|  |  | Establish Supplier Agreements | Revise the requirements (e.g., product requirements and service level requirements) to be fulfilled by the supplier to reflect negotiations with the supplier when necessary | Statements of work
|  |  |  | Document what the project will provide to the supplier | Contracts
|  |  |  | Document the supplier agreement | Memoranda of agreement
|  |  |  | Periodically review the supplier agreement to ensure it accurately reflects the project's relationship with the supplier and current risks and market conditions | Licensing agreement
Ensure that all parties to the agreement understand and agree to all requirements before implementing the agreement or any changes
Revise the supplier agreement as necessary to reflect changes to the supplier's processes or work products
Revise the project's plans and commitments, including changes to the project's processes or work products, as necessary to reflect the supplier agreement
|  | Satisfy Supplier Agreements | Execute the Supplier Agreement | Monitor supplier progress and performance (schedule, effort, cost, and technical performance) as defined in the supplier agreement | Supplier progress reports and performance measures | Supplier agreement results
|  |  |  | Conduct reviews with the supplier as specified in the supplier agreement | Supplier review materials and reports
|  |  |  | Conduct technical reviews with the supplier as defined in the supplier agreement | Action items tracked to closure
|  |  |  | Conduct management reviews with the supplier as defined in the supplier agreement | Documentation of product and document deliveries
Use the results of reviews to improve the supplier’s performance and to establish and nurture long-term relationships with preferred suppliers
Monitor risks involving the supplier and take corrective action as necessary
|  |  | Monitor Selected Supplier Processes | Identify the supplier processes that are critical to the success of the project | List of processes selected for monitoring or rationale for nonselection
|  |  |  | Monitor the selected supplier's processes for compliance with requirements of the agreement | Activity reports
|  |  |  | Analyze the results of monitoring the selected processes to detect issues as early as possible that may affect the supplier's ability to satisfy the requirements of the agreement | Performance reports
Performance curves
Discrepancy reports
|  |  | Evaluate Selected Supplier Work Products | Identify those work products that are critical to the success of the project and that should be evaluated to help detect issues early | List of work products selected for monitoring or rationale for nonselection
|  |  |  | Evaluate the selected work products | Activity reports
|  |  |  | Determine and document actions needed to address deficiencies identified in the evaluations | Discrepancy reports
|  |  | Accept the Acquired Product | Define the acceptance procedures | Acceptance test procedures
|  |  |  | Review and obtain agreement with relevant stakeholders on the acceptance procedures before the acceptance review or test | Acceptance test results
|  |  |  | Verify that the acquired products satisfy their requirements | Discrepancy reports or corrective action plans
Confirm that the nontechnical commitments associated with the acquired work product are satisfied
Document the results of the acceptance review or test
Establish and obtain supplier agreement on an action plan for any acquired work products that do not pass their acceptance review or test
Identify, document, and track action items to closure
|  |  | Transition Products | Ensure that there are appropriate facilities to receive, store, use, and maintain the acquired products | Transition plans
|  |  |  | Ensure that appropriate training is provided for those involved in receiving, storing, using, and maintaining the acquired products | Training reports
|  |  |  | Ensure that storing, distributing, and using the acquired products are performed according to the terms and conditions specified in the supplier agreement or license | Support and maintenance reports
| Measurement and Analysis (MA) | Align Measurement and Analysis Activities | Establish Measurement Objectives | Document information needs and objectives | Measurement objectives | Measurement and analysis plan
Prioritize information needs and objectives
Document, review, and update measurement objectives
Provide feedback for refining and clarifying information needs and objectives as necessary
Maintain traceability of the measurement objectives to the identified information needs and objectives
|  |  | Specify Measures | Identify candidate measures based on documented measurement objectives | Specifications of base and derived measures
Identify existing measures that already address the measurement objectives
Specify operational definitions for the measures
Prioritize, review, and update measures
|  |  | Specify Data Collection and Storage Procedures | Identify existing sources of data that are generated from current work products, processes, or transactions | Data collection and storage procedures
|  |  |  | Identify measures for which data are needed, but are not currently available | Data collection tools
Specify how to collect and store the data for each required measure
Create data collection mechanisms and process guidance
Support automatic collection of the data where appropriate and feasible
Prioritize, review, and update data collection and storage procedures
Update measures and measurement objectives as necessary
|  |  | Specify Analysis Procedures | Specify and prioritize the analyses that will be conducted and the reports that will be prepared | Analysis specifications and procedures
|  |  |  | Select appropriate data analysis methods and tools | Data analysis tools
Specify administrative procedures for analyzing the data and communicating the results
Review and update the proposed content and format of the specified analyses and reports
Update measures and measurement objectives as necessary
Specify criteria for evaluating the utility of the analysis results and for evaluating the conduct of the measurement and analysis activities
|  | Provide Measurement Results | Collect Measurement Data | Obtain the data for base measures | Base and derived measurement data sets | Measurement and analysis results
|  |  |  | Generate the data for derived measures | Results of data integrity tests
Perform data integrity checks as close to the source of the data as possible
|  |  | Analyze Measurement Data | Conduct initial analyses, interpret the results, and draw preliminary conclusions | Analysis results and draft reports
Conduct additional measurement and analysis as necessary, and prepare results for presentation
Review the initial results with relevant stakeholders
Refine criteria for future analyses
|  |  | Store Data and Results | Review the data to ensure their completeness, integrity, accuracy, and currency | Stored data inventory
Store the data according to the data storage procedures
Make the stored contents available for use only by appropriate groups and personnel
Prevent the stored information from being used inappropriately
|  |  | Communicate Results | Keep relevant stakeholders apprised of measurement results on a timely basis | Delivered reports and related analysis results
|  |  |  | Assist relevant stakeholders in understanding the results | Contextual information or guidance to aid in the interpretation of analysis results
| Process and Product Quality Assurance (PPQA) | Objectively Evaluate Processes and Work Products | Objectively Evaluate Processes | Promote an environment (created as part of project management) that encourages employee participation in identifying and reporting quality issues | Evaluation reports | Process and product assurance plan
|  |  |  | Establish and maintain clearly stated criteria for the evaluations | Noncompliance reports
|  |  |  | Use the stated criteria to evaluate performed processes for adherence to process descriptions, standards, and procedures | Corrective actions
Identify each noncompliance found during the evaluation
Identify lessons learned that could improve processes for future products and services
|  |  | Objectively Evaluate Work Products and Services | Select work products to be evaluated, based on documented sampling criteria if sampling is used | Evaluation reports
|  |  |  | Establish and maintain clearly stated criteria for the evaluation of work products | Noncompliance reports
|  |  |  | Use the stated criteria during the evaluations of work products | Corrective actions
Evaluate work products before they are delivered to the customer
Evaluate work products at selected milestones in their development
Perform in-progress or incremental evaluations of work products and services against process descriptions, standards, and procedures
Identify each case of noncompliance found during the evaluations
Identify lessons learned that could improve processes for future products and services
|  | Provide Objective Insight | Communicate and Ensure Resolution of Noncompliance Issues | Resolve each noncompliance with the appropriate members of the staff where possible | Corrective action reports | Process and product assurance results
|  |  |  | Document noncompliance issues when they cannot be resolved within the project | Evaluation reports
|  |  |  | Escalate noncompliance issues that cannot be resolved within the project to the appropriate level of management designated to receive and act on noncompliance issues | Quality trends
Analyze the noncompliance issues to see if there are any quality trends that can be identified and addressed
Ensure that relevant stakeholders are aware of the results of evaluations and the quality trends in a timely manner
Periodically review open noncompliance issues and trends with the manager designated to receive and act on noncompliance issues
Track noncompliance issues to resolution
|  |  | Establish Records | Record process and product quality assurance activities in sufficient detail such that status and results are known | Evaluation logs
|  |  |  | Revise the status and history of the quality assurance activities as necessary | Quality assurance reports
Status reports of corrective actions
Reports of quality trends
| Configuration Management (CM) | Establish Baselines | Identify Configuration Items | Select the configuration items and the work products that compose them based on documented criteria | Identified configuration items | Configuration baseline
Assign unique identifiers to configuration items
Specify the important characteristics of each configuration item
Specify when each configuration item is placed under configuration management
Identify the owner responsible for each configuration item
|  |  | Establish a Configuration Management System | Establish a mechanism to manage multiple control levels of configuration management | Configuration management system with controlled work products
|  |  |  | Store and retrieve configuration items in a configuration management system | Configuration management system access control procedures
|  |  |  | Share and transfer configuration items between control levels within the configuration management system | Change request database
Store and recover archived versions of configuration items
Store, update, and retrieve configuration management records
Create configuration management reports from the configuration management system
Preserve the contents of the configuration management system
Revise the configuration management structure as necessary
|  |  | Create or Release Baselines | Obtain authorization from the configuration control board (CCB) before creating or releasing baselines of configuration items | Baselines
|  |  |  | Create or release baselines only from configuration items in the configuration management system | Description of baselines
Document the set of configuration items that are contained in a baseline
Make the current set of baselines readily available
|  | Track and Control Changes | Track Change Requests | Initiate and record change requests in the change request database | Change requests | Configuration control results
Analyze the impact of changes and fixes proposed in the change requests
Review change requests that will be addressed in the next baseline with the relevant stakeholders and get their agreement
Track the status of change requests to closure
|  |  | Control Configuration Items | Control changes to configuration items throughout the life of the product | Revision history of configuration items
|  |  |  | Obtain appropriate authorization before changed configuration items are entered into the configuration management system | Archives of the baselines
Check in and check out configuration items from the configuration management system for incorporation of changes in a manner that maintains the correctness and integrity of the configuration items
Perform reviews to ensure that changes have not caused unintended effects on the baselines (e.g., ensure that the changes have not compromised the safety and/or security of the system)
Record changes to configuration items and the reasons for the changes as appropriate
|  | Establish Integrity | Establish Configuration Management Records | Record configuration management actions in sufficient detail so the content and status of each configuration item is known and previous versions can be recovered | Revision history of configuration items | Configuration management results
|  |  |  | Ensure that relevant stakeholders have access to and knowledge of the configuration status of the configuration items | Change log
|  |  |  | Specify the latest version of the baselines | Copy of the change requests
|  |  |  | Identify the version of configuration items that constitute a particular baseline | Status of configuration items
|  |  |  | Describe the differences between successive baselines | Differences between baselines
Revise the status and history (i.e., changes and other actions) of each configuration item as necessary
|  |  | Perform Configuration Audits | Assess the integrity of the baselines | Configuration audit results
|  |  |  | Confirm that the configuration management records correctly identify the configuration items | Action items
Review the structure and integrity of the items in the configuration management system
Confirm the completeness and correctness of the items in the configuration management system
Confirm compliance with applicable configuration management standards and procedures
Track action items from the audit to closure
1 | 7 | 15 | 56 | 219 | 139 | 15
Defined | Requirements Development (RD) | Develop Customer Requirements | Elicit Needs | Engage relevant stakeholders using methods for eliciting needs, expectations, constraints, and external interfaces |  | Customer requirements
|  |  | Develop the Customer Requirements | Translate the stakeholder needs, expectations, constraints, and interfaces into documented customer requirements | Customer requirements
|  |  |  | Define constraints for verification and validation | Customer constraints on the conduct of verification
Customer constraints on the conduct of validation
|  | Develop Product Requirements | Establish Product and Product Component Requirements | Develop requirements in technical terms necessary for product and product component design | Derived requirements | Product requirements
|  |  |  | Derive requirements that result from design decisions | Product requirements
|  |  |  | Establish and maintain relationships between requirements for consideration during change management and requirements allocation | Product component requirements
|  |  | Allocate Product Component Requirements | Allocate requirements to functions | Requirement allocation sheets
|  |  |  | Allocate requirements to product components | Provisional requirement allocations
|  |  |  | Allocate design constraints to product components | Design constraints
|  |  |  | Document relationships among allocated requirements | Derived requirements
Relationships among derived requirements
|  |  | Identify Interface Requirements | Identify interfaces both external to the product and internal to the product (i.e., between functional partitions or objects) | Interface requirements
Develop the requirements for the identified interfaces
|  | Analyze and Validate Requirements | Establish Operational Concepts and Scenarios | Develop operational concepts and scenarios that include functionality, performance, maintenance, support, and disposal as appropriate | Operational concept | Requirements analysis
|  |  |  | Define the environment in which the product or product component will operate, including boundaries and constraints | Product or product component installation, operational, maintenance, and support concepts
|  |  |  | Review operational concepts and scenarios to refine and discover requirements | Disposal concepts
|  |  |  | Develop a detailed operational concept, as products and product components are selected, that defines the interaction of the product, the end user, and the environment, and that satisfies the operational, maintenance, support, and disposal needs | Use cases
Timeline scenarios
New requirements
|  |  | Establish a Definition of Required Functionality | Analyze and quantify functionality required by end users | Functional architecture
|  |  |  | Analyze requirements to identify logical or functional partitions (e.g., subfunctions) | Activity diagrams and use cases
|  |  |  | Partition requirements into groups, based on established criteria (e.g., similar functionality, performance, or coupling), to facilitate and focus the requirements analysis | Object-oriented analysis with services or methods identified
Consider the sequencing of time-critical functions both initially and subsequently during product component development
Allocate customer requirements to functional partitions, objects, people, or support elements to support the synthesis of solutions
Allocate functional and performance requirements to functions and subfunctions
|  |  | Analyze Requirements | Analyze stakeholder needs, expectations, constraints, and external interfaces to remove conflicts and to organize into related subjects | Requirements defects reports
|  |  |  | Analyze requirements to determine whether they satisfy the objectives of higher level requirements | Proposed requirements changes to resolve defects
|  |  |  | Analyze requirements to ensure that they are complete, feasible, realizable, and verifiable | Key requirements
|  |  |  | Identify key requirements that have a strong influence on cost, schedule, functionality, risk, or performance | Technical performance measures
Identify technical performance measures that will be tracked during the development effort
Analyze operational concepts and scenarios to refine the customer needs, constraints, and interfaces and to discover new requirements
|  |  | Analyze Requirements to Achieve Balance | Use proven models, simulations, and prototyping to analyze the balance of stakeholder needs and constraints | Assessment of risks related to requirements
Perform a risk assessment on the requirements and functional architecture
Examine product lifecycle concepts for impacts of requirements on risks
|  |  | Validate Requirements | Analyze the requirements to determine the risk that the resulting product will not perform appropriately in its intended-use environment | Record of analysis methods and results
Explore the adequacy and completeness of requirements by developing product representations (e.g., prototypes, simulations, models, scenarios, and storyboards) and by obtaining feedback about them from relevant stakeholders
Assess the design as it matures in the context of the requirements validation environment to identify validation issues and expose unstated needs and customer requirements
| Technical Solution (TS) | Select Product Component Solutions | Develop Alternative Solutions and Selection Criteria | Identify screening criteria to select a set of alternative solutions for consideration | Alternative solution screening criteria | Product component solutions
|  |  |  | Identify technologies currently in use and new product technologies for competitive advantage | Evaluation reports of new technologies
|  |  |  | Identify candidate COTS products that satisfy the requirements | Alternative solutions
|  |  |  | Generate alternative solutions | Selection criteria for final selection
|  |  |  | Obtain a complete requirements allocation for each alternative | Evaluation reports of COTS products
Develop the criteria for selecting the best alternative solution
|  |  | Select Product Component Solutions | Evaluate each alternative solution/set of solutions against the selection criteria established in the context of the operating concepts and scenarios | Product component selection decisions and rationale
|  |  |  | Based on the evaluation of alternatives, assess the adequacy of the selection criteria and update these criteria as necessary | Documented relationships between requirements and product components
|  |  |  | Identify and resolve issues with the alternative solutions and requirements | Documented solutions, evaluations, and rationale
Select the best set of alternative solutions that satisfy the established selection criteria
Establish the requirements associated with the selected set of alternatives as the set of allocated requirements to those product components
Identify the product component solutions that will be reused or acquired
Establish and maintain the documentation of the solutions, evaluations, and rationale
|  | Develop the Design | Design the Product or Product Component | Establish and maintain criteria against which the design can be evaluated | Product architecture | Product design
|  |  |  | Identify, develop, or acquire the design methods appropriate for the product | Product component designs
Ensure that the design adheres to applicable design standards and criteria
Ensure that the design adheres to allocated requirements
Document the design
|  |  | Establish a Technical Data Package | Determine the number of levels of design and the appropriate level of documentation for each design level | Technical data package
Base detailed design descriptions on the allocated product component requirements, architecture, and higher level designs
Document the design in the technical data package
Document the rationale for key (i.e., significant effect on cost, schedule, or technical performance) decisions made or defined
Revise the technical data package as necessary
|  |  | Design Interfaces Using Criteria | Define interface criteria | Interface design specifications
|  |  |  | Identify interfaces associated with other product components | Interface control documents
|  |  |  | Identify interfaces associated with external items | Interface specification criteria
|  |  |  | Identify interfaces between product components and the product related lifecycle processes | Rationale for selected interface design
Apply the criteria to the interface design alternatives
Document the selected interface designs and the rationale for the selection
|  |  | Perform Make, Buy, or Reuse Analyses | Develop criteria for the reuse of product component designs | Criteria for design and product component reuse
|  |  |  | Analyze designs to determine if product components should be developed, reused, or purchased | Make-or-buy analyses
|  |  |  | Analyze implications for maintenance when considering purchased or nondevelopmental (e.g., COTS, government off the shelf, and reuse) items | Guidelines for choosing COTS product components
|  | Implement the Product Design | Implement the Design | Use effective methods to implement the product components | Implemented design | Product component
Adhere to applicable standards and criteria
Conduct peer reviews of the selected product components
Perform unit testing of the product component as appropriate
Revise the product component as necessary
|  |  | Develop Product Support Documentation | Review the requirements, design, product, and test results to ensure that issues affecting the installation, operation, and maintenance documentation are identified and resolved | End-user training materials
|  |  |  | Use effective methods to develop the installation, operation, and maintenance documentation | User's manual
|  |  |  | Adhere to the applicable documentation standards | Operator's manual
|  |  |  | Develop preliminary versions of the installation, operation, and maintenance documentation in early phases of the project lifecycle for review by the relevant stakeholders | Maintenance manual
|  |  |  | Conduct peer reviews of the installation, operation, and maintenance documentation | Online help
Revise the installation, operation, and maintenance documentation as necessary
| Product Integration (PI) | Prepare for Product Integration | Determine Integration Sequence | Identify the product components to be integrated | Product integration sequence | Product integration plan
|  |  |  | Identify the verifications to be performed during the integration of the product components | Rationale for selecting or rejecting integration sequences
Identify alternative product component integration sequences
Select the best integration sequence
Periodically review the product integration sequence and revise as needed
Record the rationale for decisions made and deferred
|  |  | Establish the Product Integration Environment | Identify the requirements for the product integration environment | Verified environment for product integration
|  |  |  | Identify verification criteria and procedures for the product integration environment | Support documentation for the product integration environment
Decide whether to make or buy the needed product integration environment
Develop an integration environment if a suitable environment cannot be acquired
Maintain the product integration environment throughout the project
Dispose of those portions of the environment that are no longer useful
|  |  | Establish Product Integration Procedures and Criteria | Establish and maintain product integration procedures for the product components | Product integration procedures
|  |  |  | Establish and maintain criteria for product component integration and evaluation | Product integration criteria
Establish and maintain criteria for validation and delivery of the integrated product
|  | Ensure Interface Compatibility | Review Interface Descriptions for Completeness | Review interface data for completeness and ensure complete coverage of all interfaces | Categories of interfaces | Interface control document
|  |  |  | Ensure that product components and interfaces are marked to ensure easy and correct connection to the joining product component | List of interfaces per category
|  |  |  | Periodically review the adequacy of interface descriptions | Mapping of the interfaces to the product components and the product integration environment
|  |  | Manage Interfaces | Ensure the compatibility of the interfaces throughout the life of the product | Table of relationships among the product components and the external environment (e.g., main power supply, fastening product, and computer bus system)
|  |  |  | Resolve conflict, noncompliance, and change issues | Table of relationships among the different product components
|  |  |  | Maintain a repository for interface data accessible to project participants | List of agreed-to interfaces defined for each pair of product components, when applicable
Reports from the interface control working group meetings
Action items for updating interfaces
Application program interface (API)
Updated interface description or agreement
|  | Assemble Product Components and Deliver the Product | Confirm Readiness of Product Components for Integration | Track the status of all product components as soon as they become available for integration | Acceptance documents for the received product components | Assembled product components
|  |  |  | Ensure that product components are delivered to the product integration environment in accordance with the product integration sequence and available procedures | Delivery receipts
|  |  |  | Confirm the receipt of each properly identified product component | Checked packing lists
|  |  |  | Ensure that each received product component meets its description | Exception reports
|  |  |  | Check the configuration status against the expected configuration | Waivers
Perform a pre-check (e.g., by a visual inspection and using basic measures) of all the physical interfaces before connecting product components together
|  |  | Assemble Product Components | Ensure the readiness of the product integration environment | Assembled product or product components
Ensure that the assembly sequence is properly performed
Revise the product integration sequence and available procedures as appropriate
|  |  | Evaluate Assembled Product Components | Conduct the evaluation of assembled product components following the product integration sequence and available procedures | Exception reports
|  |  |  | Record the evaluation results | Interface evaluation reports
Product integration summary reports
|  |  | Package and Deliver the Product or Product Component | Review the requirements, design, product, verification results, and documentation to ensure that issues affecting the packaging and delivery of the product are identified and resolved | Packaged product or product components
|  |  |  | Use effective methods to package and deliver the assembled product | Delivery documentation
Satisfy the applicable requirements and standards for packaging and delivering the product
Prepare the operational site for installation of the product
Deliver the product and related documentation and confirm receipt
Install the product at the operational site and confirm correct operation
| Verification (VER) | Prepare for Verification | Select Work Products for Verification | Identify work products for verification | Lists of work products selected for verification | Verification plan
|  |  |  | Identify the requirements to be satisfied by each selected work product | Verification methods for each selected work product
Identify the verification methods that are available for use
Define the verification methods to be used for each selected work product
Submit for integration with the project plan the identification of work products to be verified, the requirements to be satisfied, and the methods to be used
|  |  | Establish the Verification Environment | Identify verification environment requirements | Verification environment
Identify verification resources that are available for reuse and modification
Identify verification equipment and tools
Acquire verification support equipment and an environment, such as test equipment and software
|  |  | Establish Verification Procedures and Criteria | Generate the set of comprehensive, integrated verification procedures for work products and any commercial off-the-shelf products, as necessary | Verification procedures
|  |  |  | Develop and refine the verification criteria when necessary | Verification criteria
Identify the expected results, any tolerances allowed in observation, and other criteria for satisfying the requirements
Identify any equipment and environmental components needed to support verification
|  | Perform Peer Reviews | Prepare for Peer Reviews | Determine what type of peer review will be conducted | Peer review schedule | Peer review plan
|  |  |  | Define requirements for collecting data during the peer review | Peer review checklist
|  |  |  | Establish and maintain entry and exit criteria for the peer review | Entry and exit criteria for work products
|  |  |  | Establish and maintain criteria for requiring another peer review | Criteria for requiring another peer review
|  |  |  | Establish and maintain checklists to ensure that the work products are reviewed consistently | Peer review training material
|  |  |  | Develop a detailed peer review schedule, including the dates for peer review training and for when materials for peer reviews will be available | Selected work products to be reviewed
Ensure that the work product satisfies the peer review entry criteria prior to distribution
Distribute the work product to be reviewed and its related information to the participants early enough to enable participants to adequately prepare for the peer review
Assign roles for the peer review as appropriate
Prepare for the peer review by reviewing the work product prior to conducting the peer review
|  |  | Conduct Peer Reviews | Perform the assigned roles in the peer review | Peer review results
|  |  |  | Identify and document defects and other issues in the work product | Peer review issues
|  |  |  | Record the results of the peer review, including the action items | Peer review data
Collect peer review data
Identify action items and communicate the issues to relevant stakeholders
Conduct an additional peer review if the defined criteria indicate the need
Ensure that the exit criteria for the peer review are satisfied
|  |  | Analyze Peer Review Data | Record data related to the preparation, conduct, and results of the peer reviews | Peer review data
|  |  |  | Store the data for future reference and analysis | Peer review action items
Protect the data to ensure that peer review data are not used inappropriately
Analyze the peer review data
|  | Verify Selected Work Products | Perform Verification | Perform verification of selected work products against their requirements | Verification results | Verification results
|  |  |  | Record the results of verification activities | Verification reports
|  |  |  | Identify action items resulting from verification of work products | Demonstrations
|  |  |  | Document the “as-run” verification method and the deviations from the available methods and procedures discovered during its performance | As-run procedures log
|  |  | Analyze Verification Results | Compare actual results to expected results | Analysis report (e.g., statistics on performances, causal analysis of nonconformances, comparison of the behavior between the real product and models, and trends)
|  |  |  | Based on the established verification criteria, identify products that have not met their requirements or identify problems with the methods, procedures, criteria, and verification environment | Trouble reports
|  |  |  | Analyze the verification data on defects | Change requests for the verification methods, criteria, and environment
Record all results of the analysis in a report
Use verification results to compare actual measurements and performance to technical performance parameters
Provide information on how defects can be resolved (including verification methods, criteria, and verification environment) and initiate corrective action
| Validation (VAL) | Prepare for Validation | Select Products for Validation | Identify the key principles, features, and phases for product or product component validation throughout the life of the project | Lists of products and product components selected for validation | Validation plan
|  |  |  | Determine which categories of user needs (operational, maintenance, training, or support) are to be validated | Validation methods for each product or product component
|  |  |  | Select the product and product components to be validated | Requirements for performing validation for each product or product component
|  |  |  | Select the evaluation methods for product or product component validation | Validation constraints for each product or product component
Review the validation selection, constraints, and methods with relevant stakeholders
|  |  | Establish the Validation Environment | Identify validation environment requirements | Validation environment
Identify customer-supplied products
Identify reuse items
Identify test equipment and tools
Identify validation resources that are available for reuse and modification
Plan the availability of resources in detail
|  |  | Establish Validation Procedures and Criteria | Review the product requirements to ensure that issues affecting validation of the product or product component are identified and resolved | Validation procedures
|  |  |  | Document the environment, operational scenario, procedures, inputs, outputs, and criteria for the validation of the selected product or product component | Validation criteria
|  |  |  | Assess the design as it matures in the context of the validation environment to identify validation issues | Test and evaluation procedures for maintenance, training, and support
|  | Validate Product or Product Components | Perform Validation |  | Validation reports | Validation results
Validation results
Validation cross-reference matrix
As-run procedures log
Operational demonstrations
|  |  | Analyze Validation Results | Compare actual results to expected results | Validation deficiency reports
|  |  |  | Based on the established validation criteria, identify products and product components that do not perform suitably in their intended operating environments, or identify problems with the methods, criteria, and/or environment | Validation issues
|  |  |  | Analyze the validation data for defects | Procedure change request
Record the results of the analysis and identify issues
Use validation results to compare actual measurements and performance to intended use or operational need
| Organizational Process Focus (OPF) | Determine Process Improvement Opportunities | Establish Organizational Process Needs | Identify the policies, standards, and business objectives that are applicable to the organization's processes | Organization’s process needs and objectives | Appraisal findings
Examine relevant process standards and models for best practices
Determine the organization’s process-performance objectives
Define the essential characteristics of the organization’s processes
Document the organization’s process needs and objectives
Revise the organization’s process needs and objectives as needed
|  |  | Appraise the Organization’s Processes | Obtain sponsorship of the process appraisal from senior management | Plans for the organization's process appraisals CMMI for Development
|  |  |  | Define the scope of the process appraisal | Appraisal findings that address strengths and weaknesses of the organization's processes
|  |  |  | Determine the method and criteria for process appraisal | Improvement recommendations for the organization's processes
Plan, schedule, and prepare for the process appraisal
Conduct the process appraisal
Document and deliver the appraisal’s activities and findings
|  |  | Identify the Organization's Process Improvements | Determine candidate process improvements | Analysis of candidate process improvements
|  |  |  | Prioritize the candidate process improvements | Identification of improvements for the organization's processes
Identify and document the process improvements that will be implemented
Revise the list of planned process improvements to keep it current
|  | Plan and Implement Process Improvements | Establish Process Action Plans | Identify strategies, approaches, and actions to address the identified process improvements | Organization's approved process action plans | Process improvement plan
Establish process action teams to implement the actions
Document process action plans
Review and negotiate process action plans with relevant stakeholders
Review process action plans as necessary
|  |  | Implement Process Action Plans | Make process action plans readily available to relevant stakeholders | Commitments among the various process action teams
|  |  |  | Negotiate and document commitments among the process action teams and revise their process action plans as necessary | Status and results of implementing process action plans
|  |  |  | Track progress and commitments against process action plans | Plans for pilots
Conduct joint reviews with the process action teams and relevant stakeholders to monitor the progress and results of the process actions
Plan pilots needed to test selected process improvements
Review the activities and work products of process action teams
Identify, document, and track to closure issues in implementing process action plans
Ensure that the results of implementing process action plans satisfy the organization’s process improvement objectives
|  | Deploy Organizational Process Assets and Incorporate Lessons Learned | Deploy Organizational Process Assets | Deploy organizational process assets across the organization | Plans for deploying organizational process assets and changes to them across the organization | Process improvement results
|  |  |  | Document the changes to the organizational process assets | Training materials for deploying organizational process assets and changes to them
|  |  |  | Deploy the changes that were made to the organizational process assets across the organization | Documentation of changes to organizational process assets
|  |  |  | Provide guidance and consultation on the use of the organizational process assets | Support materials for deploying organizational process assets and changes to them
|  |  | Deploy Standard Processes | Identify projects within the organization that are starting up | Organization's list of projects and status of process deployment on each project (i.e., existing and planned projects)
|  |  |  | Identify active projects that would benefit from implementing the organization’s current set of standard processes | Guidelines for deploying the organization’s set of standard processes on new projects
|  |  |  | Establish plans to implement the organization’s current set of standard processes on the identified projects | Records of tailoring the organization’s set of standard processes and implementing them on identified projects
Assist projects in tailoring the organization’s set of standard processes to meet project needs
Maintain records of tailoring and implementing processes on the identified projects
Ensure that the defined processes resulting from process tailoring are incorporated into the plans for process-compliance audits
As the organization’s set of standard processes are updated, identify which projects should implement the changes
|  |  | Monitor Implementation | Monitor projects for their use of the organization’s process assets and changes to them | Results of monitoring process implementation on projects
|  |  |  | Review selected process artifacts created during the life of each project | Status and results of process-compliance evaluations
|  |  |  | Review the results of process-compliance evaluations to determine how well the organization’s set of standard processes has been deployed | Results of reviewing selected process artifacts created as part of process tailoring and implementation
Identify, document, and track to closure issues related to implementing the organization’s set of standard processes
|  |  | Incorporate Process-Related Experiences into the Organizational Process Assets | Conduct periodic reviews of the effectiveness and suitability of the organization’s set of standard processes and related organizational process assets relative to the organization’s business objectives | Process improvement proposals
|  |  |  | Obtain feedback about the use of the organizational process assets | Process lessons learned
|  |  |  | Derive lessons learned from defining, piloting, implementing, and deploying the organizational process assets | Measurements on the organizational process assets
|  |  |  | Make available lessons learned to the people in the organization as appropriate | Improvement recommendations for the organizational process assets
|  |  |  | Analyze the organization's common set of measures | Records of the organization's process improvement activities
|  |  |  | Appraise the processes, methods, and tools in use in the organization and develop recommendations for improving the organizational process assets | Information on the organizational process assets and improvements to them
Make the best of the organization's processes, methods, and tools available to the people in the organization as appropriate
Manage process improvement proposals
Establish and maintain records of the organization's process improvement activities
| Organizational Process Definition (OPD) | Establish Organizational Process Assets | Establish Standard Processes | Decompose each standard process into constituent process elements to the detail needed to understand and describe the process | Organization's set of standard processes | Organizational process assets
Specify the critical attributes of each process element
Specify the relationships of the process elements
Ensure that the organization's set of standard processes adheres to applicable policies, standards, and models
Ensure that the organization’s set of standard processes satisfies the process needs and objectives of the organization
Ensure that there is appropriate integration among the processes that are included in the organization’s set of standard processes
Document the organization's set of standard processes
Conduct peer reviews on the organization's set of standard processes
Revise the organization's set of standard processes as necessary
|  |  | Establish Lifecycle Model Descriptions | Select lifecycle models based on the needs of projects and the organization | Descriptions of lifecycle models
Document the descriptions of the lifecycle models
Conduct peer reviews on the lifecycle models
Revise the descriptions of the lifecycle models as necessary
|  |  | Establish Tailoring Criteria and Guidelines | Specify the selection criteria and procedures for tailoring the organization's set of standard processes | Tailoring guidelines for the organization's set of standard processes
Specify the standards for documenting the defined processes
Specify the procedures for submitting and obtaining approval of waivers from the requirements of the organization’s set of standard processes
Document the tailoring guidelines for the organization's set of standard processes
Conduct peer reviews on the tailoring guidelines
Revise the tailoring guidelines as necessary
|  |  | Establish the Organization’s Measurement Repository | Determine the organization's needs for storing, retrieving, and analyzing measurements | Definition of the common set of product and process measures for the organization’s set of standard processes
|  |  |  | Define a common set of process and product measures for the organization's set of standard processes | Design of the organization’s measurement repository
|  |  |  | Design and implement the measurement repository | Organization's measurement repository (that is, the repository structure and support environment)
|  |  |  | Specify the procedures for storing, updating, and retrieving measures | Organization’s measurement data
Conduct peer reviews on the definitions of the common set of measures and the procedures for storing and retrieving measures
Enter the specified measures into the repository
Make the contents of the measurement repository available for use by the organization and projects as appropriate
Revise the measurement repository, common set of measures, and procedures as the organization’s needs change
|  |  | Establish the Organization’s Process Asset Library | Design and implement the organization’s process asset library, including the library structure and support environment | Design of the organization’s process asset library
|  |  |  | Specify the criteria for including items in the library | Organization's process asset library
|  |  |  | Specify the procedures for storing and retrieving items | Selected items to be included in the organization’s process asset library
|  |  |  | Enter the selected items into the library and catalog them for easy reference and retrieval | Catalog of items in the organization’s process asset library
Make the items available for use by the projects
Periodically review the use of each item and use the results to maintain the library contents
Revise the organization’s process asset library as necessary
|  |  | Establish Work Environment Standards | Evaluate commercially-available work environment standards appropriate for the organization | Work environment standards
Adopt existing work environment standards and develop new ones to fill gaps based on the organization’s process needs and objectives
|  | Enable IPPD Management | Establish Empowerment Mechanisms | Determine rules and guidelines for the degree of empowerment provided to people and integrated teams | Empowerment rules and guidelines for people and integrated teams | Integrated teaming process
|  |  |  | Determine rules and guidelines for the use of different decision types in making various kinds of team decisions | Decision-making rules and guidelines
|  |  |  | Define the process for using the decision-making rules and guidelines | Issue resolution documentation
Define a process for issue resolution when an issue cannot be decided at the level at which it arose
Maintain the empowerment mechanisms and the rules and guidelines for decision making
|  |  | Establish Rules and Guidelines for Integrated Teams | Establish rules and guidelines for structuring and forming integrated teams | Rules and guidelines for the structuring and formation of integrated teams
Define the expectations, rules, and guidelines that will guide how the integrated teams work collectively
Maintain the rules and guidelines for structuring and forming integrated teams
|  |  | Balance Team and Home Organization Responsibilities | Establish guidelines for home organization responsibilities that promote integrated team behavior | Organizational guidelines for balancing team and home organization responsibilities
|  |  |  | Establish guidelines for team management responsibilities to ensure integrated team members report appropriately to their home organizations | Performance review process that considers both functional supervisor and team leader input
Establish a performance review process that considers input from both home organization and integrated team leaders
Maintain the guidelines for balancing team and home organization responsibilities
| Organizational Training (OT) | Establish an Organizational Training Capability | Establish the Strategic Training Needs | Analyze the organization’s strategic business objectives and process improvement plan to identify potential future training needs | Training needs | Training plan
|  |  |  | Document the strategic training needs of the organization | Assessment analysis
Determine the roles and skills needed to perform the organization’s set of standard processes
Document the training needed to perform the roles in the organization’s set of standard processes
Document the training needed to maintain the safe, secure and continued operation of the business
Revise the organization’s strategic needs and required training as necessary
|  |  | Determine Which Training Needs Are the Responsibility of the Organization | Analyze the training needs identified by the various projects and support groups | Common project and support group training needs
|  |  |  | Negotiate with the various projects and support groups on how their specific training needs will be satisfied | Training commitments
Document the commitments for providing training support to the projects and support groups
|  |  | Establish an Organizational Training Tactical Plan | Establish plan content | Organizational training tactical plan
Establish commitments to the plan
Revise plan and commitments as necessary
|  |  | Establish Training Capability | Select the appropriate approaches to satisfy specific organizational training needs | Training materials and supporting artifacts
Determine whether to develop training materials internally or acquire them externally
Develop or obtain training materials
Develop or obtain qualified instructors
Describe the training in the organization's training curriculum
Revise the training materials and supporting artifacts as necessary
|  | Provide Necessary Training | Deliver Training | Select the people who will receive the training necessary to perform their roles effectively | Delivered training course | Training results
Schedule the training, including any resources, as necessary (e.g., facilities and instructors)
Conduct the training
Track the delivery of training against the plan
|  |  | Establish Training Records | Keep records of all students who successfully complete each training course or other approved training activity as well as those who are unsuccessful | Training records
|  |  |  | Keep records of all staff who have been waived from specific training | Training updates to the organizational repository
Keep records of all students who successfully complete their designated required training
Make training records available to the appropriate people for consideration in assignments
|  |  | Assess Training Effectiveness | Assess in-progress or completed projects to determine whether staff knowledge is adequate for performing project tasks | Training-effectiveness surveys
|  |  |  | Provide a mechanism for assessing the effectiveness of each training course with respect to established organizational, project, or individual learning (or performance) objectives | Training program performance assessments
|  |  |  | Obtain student evaluations of how well training activities met their needs | Instructor evaluation forms
Training examinations
| Integrated Project Management (IPM) | Use the Project’s Defined Process | Establish the Project’s Defined Process | Select a lifecycle model from those available from the organizational process assets | The project’s defined process | Project's defined process
Select the standard processes from the organization's set of standard processes that best fit the needs of the project
Tailor the organization’s set of standard processes and other organizational process assets according to the tailoring guidelines to produce the project’s defined process
Use other artifacts from the organization's process asset library as appropriate
Document the project's defined process
Conduct peer reviews of the project's defined process
Revise the project's defined process as necessary
|  |  | Use Organizational Process Assets for Planning Project Activities | Use the tasks and work products of the project's defined process as a basis for estimating and planning the project's activities | Project estimates
|  |  |  | Use the organization’s measurement repository in estimating the project’s planning parameters | Project plans
|  |  | Establish the Project's Work Environment | Plan, design, and install a work environment for the project | Equipment and tools for the project
|  |  |  | Provide ongoing maintenance and operational support for the project’s work environment | Installation, operation, and maintenance manuals for the project work environment
|  |  |  | Maintain the qualification of the components of the project’s work environment | User surveys and results
|  |  |  | Periodically review how well the work environment is meeting the project’s needs and supporting collaboration, and take action as appropriate | Usage, performance, and maintenance records
Support services for the project’s work environment
|  |  | Integrate Plans | Integrate other plans that affect the project with the project plan | Integrated plans
Incorporate into the project plan the definitions of measures and measurement activities for managing the project
Identify and analyze product and project interface risks
Schedule the tasks in a sequence that accounts for critical development factors and project risks
Incorporate the plans for performing peer reviews on the work products of the project's defined process
Incorporate the training needed to perform the project’s defined process in the project’s training plans
Establish objective entry and exit criteria to authorize the initiation and completion of the tasks described in the work breakdown structure (WBS)
Ensure that the project plan is appropriately compatible with the plans of relevant stakeholders
Identify how conflicts will be resolved that arise among relevant stakeholders
|  |  | Manage the Project Using the Integrated Plans | Implement the project’s defined process using the organization's process asset library | Work products created by performing the project’s defined process
|  |  |  | Monitor and control the project’s activities and work products using the project’s defined process, project plan, and other plans that affect the project | Collected measures ("actuals") and progress records or reports
|  |  |  | Obtain and analyze the selected measures to manage the project and support the organization’s needs | Revised requirements, plans, and commitments
|  |  |  | Periodically review and align the project’s performance with the current and anticipated needs, objectives, and requirements of the organization, customer, and end users, as appropriate | Integrated plans
|  |  | Contribute to the Organizational Process Assets | Propose improvements to the organizational process assets | Proposed improvements to the organizational process assets
|  |  |  | Store process and product measures in the organization’s measurement repository | Actual process and product measures collected from the project
|  |  |  | Submit documentation for possible inclusion in the organization's process asset library | Documentation (e.g., exemplary process descriptions, plans, training modules, checklists, and lessons learned)
|  |  |  | Document lessons learned from the project for inclusion in the organization's process asset library | Process artifacts associated with tailoring and implementing the organization’s set of standard processes on the project
Provide process artifacts associated with tailoring and implementing the organization’s set of standard processes in support of the organization’s process monitoring activities
|  | Coordinate and Collaborate with Relevant Stakeholders | Manage Stakeholder Involvement | Coordinate with the relevant stakeholders who should participate in the project’s activities | Agendas and schedules for collaborative activities | Stakeholder involvement results
|  |  |  | Ensure that work products that are produced to satisfy commitments meet the requirements of the recipient projects | Documented issues (e.g., issues with customer requirements, product and product component requirements, product architecture, and product design)
|  |  |  | Develop recommendations and coordinate the actions to resolve misunderstandings and problems with the product and product component requirements, product and product component architecture, and product and product component design | Recommendations for resolving relevant stakeholder issues
|  |  | Manage Dependencies | Conduct reviews with relevant stakeholders | Defects, issues, and action items resulting from reviews with relevant stakeholders
|  |  |  | Identify each critical dependency | Critical dependencies
|  |  |  | Establish need dates and plan dates for each critical dependency based on the project schedule | Commitments to address critical dependencies
|  |  |  | Review and get agreement on the commitments to address each critical dependency with the people responsible for providing the work product and the people receiving the work product | Status of critical dependencies
Document the critical dependencies and commitments
Track the critical dependencies and commitments and take corrective action as appropriate
|  |  | Resolve Coordination Issues | Identify and document issues | Relevant stakeholder coordination issues
|  |  |  | Communicate issues to the relevant stakeholders | Status of relevant stakeholder coordination issues
Resolve issues with the relevant stakeholders
Escalate to the appropriate managers those issues not resolvable with the relevant stakeholders
Track the issues to closure
Communicate with the relevant stakeholders on the status and resolution of the issues
|  | Apply IPPD Principles | Establish the Project’s Shared Vision | Articulate the project’s shared vision in terms of purpose or mission, vision, values, and objectives | Documented shared vision | Integrated teaming plan
|  |  |  | Reach consensus on the project’s shared vision | Communications strategy
|  |  |  | Establish a strategy to communicate the project’s shared vision both externally and internally | Published principles, shared vision statement, mission statement, and objectives (e.g., posters, wallet cards, and presentations)
Create presentations suitable for the various audiences that need to be informed about the project’s shared vision
Ensure that project and individual activities and tasks are aligned with the project’s shared vision
|  |  | Establish the Integrated Team Structure | Establish an integrated team structure | Assessments of the product and product architectures, including risk and complexity
|  |  |  | Periodically evaluate and modify the integrated team structure to best meet project needs | Integrated team structure
|  |  | Allocate Requirements to Integrated Teams | Allocate the tasks, responsibilities, and work products to be delivered, and the associated requirements and interfaces to the appropriate integrated teams | Responsibilities allocated to each integrated team
|  |  |  | Check that the distribution of requirements and interfaces covers all specified product requirements and other requirements | Work product requirements, technical interfaces, and business (e.g., cost accounting and project management) interfaces each integrated team will be responsible for satisfying
|  |  |  | Designate the sponsor for each integrated team | List of integrated team sponsors
|  |  | Establish Integrated Teams | Choose a leader for each integrated team | List of team leaders
|  |  |  | Allocate resources to each integrated team | List of team members assigned to each integrated team
|  |  |  | Charter each integrated team | Integrated team charters
|  |  |  | Review the composition of an integrated team and its place in the integrated team structure when its team leader changes or another significant change of membership occurs | Measures for evaluating the performance of integrated teams
|  |  |  | Review the composition of a team and its tasking when a change in team responsibility occurs | Periodic integrated team status reports
Manage the overall performance of the teams
|  |  | Ensure Collaboration among Interfacing Teams | Establish and maintain the boundaries of work product ownership among interfacing teams within the project or organization | Work product ownership agreements
|  |  |  | Establish and maintain interfaces and processes among interfacing teams for the exchange of inputs, outputs, or work products | Team work plans
|  |  |  | Develop, communicate, and distribute among interfacing teams the commitment lists and work plans that are related to work product or team interfaces | Commitment lists
| Risk Management (RM) | Prepare for Risk Management | Determine Risk Sources and Categories | Determine risk sources | Risk source lists (external and internal) | Risk management strategy
|  |  |  | Determine risk categories | Risk categories list
|  |  | Define Risk Parameters | Define consistent criteria for evaluating and quantifying risk likelihood and severity levels | Risk evaluation, categorization, and prioritization criteria
|  |  |  | Define thresholds for each risk category | Risk management requirements (e.g., control and approval levels, and reassessment intervals)
Define bounds on the extent to which thresholds are applied against or within a category
|  |  | Establish a Risk Management Strategy |  | Project risk management strategy
|  | Identify and Analyze Risks | Identify Risks | Identify the risks associated with cost, schedule, and performance | List of identified risks, including the context, conditions, and consequences of risk occurrence | Risk list
Review environmental elements that may impact the project
Review all elements of the work breakdown structure as part of identifying risks to help ensure that all aspects of the work effort have been considered
Review all elements of the project plan as part of identifying risks to help ensure that all aspects of the project have been considered
Document the context, conditions, and potential consequences of the risk
Identify the relevant stakeholders associated with each risk
|  |  | Evaluate, Categorize, and Prioritize Risks | Evaluate the identified risks using the defined risk parameters | List of risks, with a priority assigned to each risk
Categorize and group risks according to the defined risk categories
Prioritize risks for mitigation
|  | Mitigate Risks | Develop Risk Mitigation Plans | Determine the levels and thresholds that define when a risk becomes unacceptable and triggers the execution of a risk mitigation plan or a contingency plan | Documented handling options for each identified risk | Risk mitigation results
|  |  |  | Identify the person or group responsible for addressing each risk | Risk mitigation plans
|  |  |  | Determine the cost-to-benefit ratio of implementing the risk mitigation plan for each risk | Contingency plans
|  |  |  | Develop an overall risk mitigation plan for the project to orchestrate the implementation of the individual risk mitigation and contingency plans | List of those responsible for tracking and addressing each risk
Develop contingency plans for selected critical risks in the event their impacts are realized
|  |  | Implement Risk Mitigation Plans | Monitor risk status | Updated lists of risk status
|  |  |  | Provide a method for tracking open risk-handling action items to closure | Updated assessments of risk likelihood, consequence, and thresholds
|  |  |  | Invoke selected risk-handling options when monitored risks exceed the defined thresholds | Updated lists of risk-handling options
|  |  |  | Establish a schedule or period of performance for each risk handling activity that includes the start date and anticipated completion date | Updated list of actions taken to handle risks
|  |  |  | Provide continued commitment of resources for each plan to allow successful execution of the risk-handling activities | Risk mitigation plans
Collect performance measures on the risk-handling activities
| Decision Analysis and Resolution (DAR) | Evaluate Alternatives | Establish Guidelines for Decision Analysis | Establish guidelines | Guidelines for when to apply a formal evaluation process | Decision analysis and resolution plan
Incorporate the use of the guidelines into the defined process where appropriate
|  |  | Establish Evaluation Criteria | Define the criteria for evaluating alternative solutions | Documented evaluation criteria | Decision analysis and resolution results
|  |  |  | Define the range and scale for ranking the evaluation criteria | Rankings of criteria importance
Rank the criteria
Assess the criteria and their relative importance
Evolve the evaluation criteria to improve their validity
Document the rationale for the selection and rejection of evaluation criteria
|  |  | Identify Alternative Solutions | Perform a literature search | Identified alternatives
Identify alternatives for consideration in addition to those that may be provided with the issue
Document the proposed alternatives
|  |  | Select Evaluation Methods | Select the methods based on the purpose for analyzing a decision and on the availability of the information used to support the method | Selected evaluation methods
Select evaluation methods based on their ability to focus on the issues at hand without being overly influenced by side issues
Determine the measures needed to support the evaluation method
|  |  | Evaluate Alternatives | Evaluate the proposed alternative solutions using the established evaluation criteria and selected methods | Evaluation results
Evaluate the assumptions related to the evaluation criteria and the evidence that supports the assumptions
Evaluate whether uncertainty in the values for alternative solutions affects the evaluation and address as appropriate
Perform simulations, modeling, prototypes, and pilots as necessary to exercise the evaluation criteria, methods, and alternative solutions
Consider new alternative solutions, criteria, or methods if the proposed alternatives do not test well; repeat the evaluations until alternatives do test well
Document the results of the evaluation
|  |  | Select Solutions | Assess the risks associated with implementing the recommended solution | Recommended solutions to address significant issues
Document the results and rationale for the recommended solution
1 | 11 | 28 | 92 | 420 | 239 | 29
Quantitatively Managed | Organizational Process Performance (OPP) | Establish Performance Baselines and Models | Select Processes |  | List of processes or subprocesses identified for process performance analyses | Process performance baseline
|  |  | Establish Process-Performance Measures | Determine which of the organization’s business objectives for quality and process performance need to be addressed by the measures | Definitions for the selected measures of process performance
Select measures that provide appropriate insight into the organization’s quality and process performance
Incorporate the selected measures into the organization’s set of common measures
Revise the set of measures as necessary
|  |  | Establish Quality and Process-Performance Objectives | Review the organization’s business objectives related to quality and process performance | Organization's quality and process-performance objectives
Define the organization’s quantitative objectives for quality and process performance
Define the priorities of the organization’s objectives for quality and process performance
Review, negotiate, and obtain commitment for the organization’s quality and process-performance objectives and their priorities from the relevant stakeholders
Revise the organization’s quantitative objectives for quality and process performance as necessary
|  |  | Establish Process-Performance Baselines | Collect measurements from the organization’s projects | Baseline data on the organization’s process performance
Establish and maintain the organization’s process-performance baselines from the collected measurements and analyses
Review and get agreement with relevant stakeholders about the organization's process-performance baselines
Make the organization's process-performance information available across the organization in the organization's measurement repository
Compare the organization’s process-performance baselines to the associated objectives
Revise the organization’s process-performance baselines as necessary
|  |  | Establish Process-Performance Models | Establish the process-performance models based on the organization’s set of standard processes and the organization’s process-performance baselines | Process-performance models | Process performance model
Calibrate the process-performance models based on the organization’s past results and current needs
Review the process-performance models and get agreement with relevant stakeholders
Support the projects’ use of the process-performance models
Revise the process-performance models as necessary
| Quantitative Project Management (OPM) | Quantitatively Manage the Project | Establish the Project’s Objectives | Review the organization's objectives for quality and process performance | The project’s quality and process-performance objectives | Quantitative management plan
Identify the quality and process performance needs and priorities of the customer, suppliers, end users, and other relevant stakeholders
Identify how process performance is to be measured
Define and document measurable quality and process performance objectives for the project
Derive interim objectives for each lifecycle phase, as appropriate, to monitor progress toward achieving the project’s objectives
Resolve conflicts among the project’s quality and processperformance objectives (e.g., if one objective cannot be achieved without compromising another objective)
Establish traceability to the project’s quality and process performance objectives from their sources
Define and negotiate quality and process-performance objectives for suppliers
Revise the project’s quality and process-performance objectives as necessary
|  |  | Compose the Defined Process | Establish the criteria to use in identifying which subprocesses are valid candidates for use | Criteria used in identifying which subprocesses are valid candidates for inclusion in the project’s defined process
|  |  |  | Determine whether the subprocesses that are to be statistically managed, and that were obtained from the organizational process assets, are suitable for statistical management | Candidate subprocesses for inclusion in the project’s defined process
|  |  |  | Analyze the interaction of subprocesses to understand the relationships among the subprocesses and the measured attributes of the subprocesses | Subprocesses to be included in the project’s defined process
|  |  |  | Identify the risk when no subprocess is available that is known to be capable of satisfying the quality and process-performance objectives (i.e., no capable subprocess is available or the capability of the subprocess is not known) | Identified risks when selected subprocesses lack a process performance history
|  |  | Select the Subprocesses that Will Be Statistically Managed | Identify which of the quality and process-performance objectives of the project will be statistically managed | Quality and process-performance objectives that will be addressed by statistical management
|  |  |  | Identify the criteria to be used in selecting the subprocesses that are the main contributors to achieving the identified quality and process-performance objectives and for which predictable performance is important | Criteria used in selecting which subprocesses will be statistically managed
|  |  |  | Select the subprocesses that will be statistically managed using the selection criteria | Subprocesses that will be statistically managed
|  |  |  | Identify the product and process attributes of the selected subprocesses that will be measured and controlled | Identified process and product attributes of the selected subprocesses that should be measured and controlled
|  |  | Manage Project Performance | Periodically review the performance of each subprocess and the capability of each subprocess selected to be statistically managed to appraise progress toward achieving the project’s quality and process-performance objectives | Estimates (predictions) of the achievement of the project’s quality and process-performance objectives
|  |  |  | Periodically review the actual results achieved against established interim objectives for each phase of the project lifecycle to appraise progress toward achieving the project’s quality and processperformance objectives | Documentation of the risks in achieving the project’s quality and process-performance objectives
|  |  |  | Track suppliers’ results for achieving their quality and process performance objectives | Documentation of actions needed to address the deficiencies in achieving the project’s objectives
Use process-performance models calibrated with obtained measures of critical attributes to estimate progress toward achieving the project’s quality and process-performance objectives
Identify and manage the risks associated with achieving the project’s quality and process-performance objectives
Determine and document actions needed to address the deficiencies in achieving the project’s quality and process performance objectives
|  | Statistically Manage Subprocess Performance | Select Measures and Analytic Techniques | Identify common measures from the organizational process assets that support statistical management | Definitions of the measures and analytic techniques to be used in (or proposed for) statistically managing the subprocesses | Quantitative management results
|  |  |  | Identify additional measures that may be needed for this instance to cover critical product and process attributes of the selected subprocesses | Operational definitions of the measures, their collection points in the subprocesses, and how the integrity of the measures will be determined
|  |  |  | Identify the measures that are appropriate for statistical management | Traceability of measures back to the project’s quality and process performance objectives
|  |  |  | Specify the operational definitions of the measures, their collection points in the subprocesses, and how the integrity of the measures will be determined | Instrumented organizational support environment to support automatic data collection
Analyze the relationship of the identified measures to the organization’s and project’s objectives, and derive objectives that state specific target measures or ranges to be met for each measured attribute of each selected subprocess
Instrument the organizational support environment to support collection, derivation, and analysis of statistical measures
Identify the appropriate statistical analysis techniques that are expected to be useful in statistically managing the selected subprocesses
Revise the measures and statistical analysis techniques as necessary
|  |  | Apply Statistical Methods to Understand Variation | Establish trial natural bounds for subprocesses having suitable historical performance data | Collected measures
|  |  |  | Collect data, as defined by the selected measures, on the subprocesses as they execute | Natural bounds of process performance for each measured attribute of each selected subprocess
|  |  |  | Calculate the natural bounds of process performance for each measured attribute | Process performance compared to the natural bounds of process performance for each measured attribute of each selected subprocess
Identify special causes of variation
Analyze the special cause of process variation to determine the reasons the anomaly occurred
Determine what corrective action should be taken when special causes of variation are identified
Recalculate the natural bounds for each measured attribute of the selected subprocesses as necessary
|  |  | Monitor Performance of the Selected Subprocesses | Compare the quality and process-performance objectives to the natural bounds of the measured attribute | Natural bounds of process performance for each selected subprocess compared to its established (derived) objectives
|  |  |  | Monitor changes in quality and process-performance objectives and selected subprocess’ process capability | For each subprocess, its process capability
|  |  |  | Identify and document subprocess capability deficiencies | For each subprocess, the actions needed to address deficiencies in its process capability
Determine and document actions needed to address subprocess capability deficiencies
|  |  | Record Statistical Management Data |  | Statistical and quality management data recorded in the organization’s measurement repository
1 | 2 | 3 | 13 | 62 | 28 | 4
Optimizing | Organizational Innovation and Deployment (OID) | Select Improvements | Collect and Analyze Improvement Proposals | Collect process- and technology-improvement proposals | Analyzed process- and technology-improvement proposals | Process and technology improvement proposals
Analyze the costs and benefits of process- and technology improvement proposals as appropriate
Identify the process- and technology-improvement proposals that are innovative
Identify potential barriers and risks to deploying each process- and technology-improvement proposal
Estimate the cost, effort, and schedule required for deploying each process- and technology-improvement proposal
Select the process- and technology-improvement proposals to be piloted before broadscale deployment
Document the results of the evaluation of each process- and technology-improvement proposal
Monitor the status of each process- and technology-improvement proposal
|  |  | Identify and Analyze Innovations | Analyze the organization's set of standard processes to determine areas where innovative improvements would be most helpful | Candidate innovative improvements
|  |  |  | Investigate innovative improvements that may improve the organization's set of standard processes | Analysis of proposed innovative improvements
Analyze potential innovative improvements to understand their effects on process elements and predict their influence on the process
Analyze the costs and benefits of potential innovative improvements
Create process- and technology-improvement proposals for those innovative improvements that would result in improving the organization's processes or technologies
Select the innovative improvements to be piloted before broadscale deployment
Document the results of the evaluations of innovative improvements
|  |  | Pilot Improvements | Plan the pilots | Pilot evaluation reports
|  |  |  | Review and get relevant stakeholder agreement on the plans for the pilots | Documented lessons learned from pilots
Consult with and assist the people performing the pilots
Perform each pilot in an environment that is characteristic of the environment present in a broadscale deployment
Track the pilots against their plans
Review and document the results of pilots
|  |  | Select Improvements for Deployment | Prioritize the candidate process and technology improvements for deployment | Process and technology improvements selected for deployment
Select the process and technology improvements to be deployed
Determine how each process and technology improvement will be deployed
Document the results of the selection process
|  | Deploy Improvements | Plan the Deployment | Determine how each process and technology improvement must be adjusted for organization-wide deployment | Deployment plan for selected process and technology improvements | Process and technology improvement results
Determine the changes necessary to deploy each process and technology improvement
Identify strategies to address potential barriers to deploying each process and technology improvement
Establish measures and objectives for determining the value of each process and technology improvement with respect to the organization’s quality and process-performance objectives
Document the plan for deploying each process and technology improvement
Review and get agreement with relevant stakeholders on the plan for deploying each process and technology improvement
Revise the plan for deploying each process and technology improvement as necessary
|  |  | Manage the Deployment | Monitor the deployment of the process and technology improvements using the deployment plan | Updated training materials (to reflect deployed process and technology improvements)
|  |  |  | Coordinate the deployment of process and technology improvements across the organization | Documented results of process- and technology-improvement deployment activities
|  |  |  | Quickly deploy process and technology improvements in a controlled and disciplined manner, as appropriate | Revised process- and technology-improvement measures, objectives, priorities, and deployment plans
Incorporate the process and technology improvements into organizational process assets, as appropriate
Coordinate the deployment of the process and technology improvements into the projects' defined processes as appropriate
Provide consulting, as appropriate, to support deployment of the process and technology improvements
Provide updated training materials to reflect the improvements to the organizational process assets
Confirm that the deployment of all process and technology improvements is completed
Determine whether the ability of the defined process to meet quality and process-performance objectives is adversely affected by the process and technology improvement, and take corrective action as necessary
Document and review the results of process- and technologyimprovement deployment
|  |  | Measure Improvement Effects | Measure the actual cost, effort, and schedule for deploying each process and technology improvement | Documented measures of the effects resulting from the deployed process and technology improvements
Measure the value of each process and technology improvement
Measure the progress toward achieving the organization's quality and process-performance objectives
Analyze the progress toward achieving the organization's quality and process-performance objectives and take corrective action as needed
Store the measures in the organization’s measurement repository
| Causal Analysis and Resolution (CAR) | Determine Causes of Defects | Select Defect Data for Analysis | Gather relevant defect or problem data | Defect and problem data selected for further analysis | Action proposals
Determine which defects and other problems will be analyzed further
|  |  | Analyze Causes | Conduct causal analysis with the people who are responsible for performing the task | Action proposal
Analyze selected defects and other problems to determine their root causes
Group the selected defects and other problems based on their root causes
Propose and document actions that need to be taken to prevent the future occurrence of similar defects or other problems
|  | Address Causes of Defects | Implement the Action Proposals | Analyze the action proposals and determine their priorities | Action proposals selected for implementation | Action proposal results
|  |  |  | Select the action proposals that will be implemented | Improvement proposals
Create action items for implementing the action proposals
Identify and remove similar defects that may exist in other processes and work products
Identify and document improvement proposals for the organization’s set of standard processes
|  |  | Evaluate the Effect of Changes | Measure the change in the performance of the project's defined process as appropriate | Measures of performance and performance change
Measure the capability of the project's defined process as appropriate
|  |  | Record Data |  | Causal analysis and resolution records
1 | 2 | 4 | 11 | 60 | 16 | 4